Piter Garcia & Daniel Krutz - Research Task Tracker

Complete Timed/Logged Task Log

August 2025 - January 2026

Document Type: Formal Task Tracker with Timing & Logging
Period Covered: August 11, 2025 - January 8, 2026
Last Updated: January 8, 2026, 1:04 AM EST
Owner: Piter Garcia (GA) / Daniel Krutz (Faculty Advisor)
Project: Quantum Entanglement Path Selection using ML Bandits

EXECUTIVE SUMMARY

| Metric | Value |
| --- | --- |
| Total Tasks Logged | 56 |
| Completed Tasks | 48 |
| In Progress Tasks | 5 |
| Awaiting Response | 3 |
| Completion Rate | 85.7% |
| Project Status | Paper Finalization & Team Alignment |
| Paper Completion | ~90% |
| Framework Status | Production-Ready |

TASK LOG - CHRONOLOGICAL RECORD

AUGUST 2025

Task 1: GA Position Initiation

| Property | Details |
| --- | --- |
| Task ID | T-2025-001 |
| Task Date/Time | August 11, 2025 |
| Assigned By | Daniel Krutz |
| Assigned To | Piter Garcia |
| Status | ✅ COMPLETED |
| Task Type | Organizational |
| Description | Welcome Piter Garcia as Graduate Assistant; initiate research in quantum computing domain |
| Deliverable | GA position acceptance and initial orientation |
| Logged Time | <1 hour |
| Completion Date | August 11, 2025 |

Task 2: Literature Review - Jie Xu Paper Analysis

| Property | Details |
| --- | --- |
| Task ID | T-2025-002 |
| Task Date/Time | August 20-25, 2025 |
| Assigned By | Daniel Krutz |
| Assigned To | Piter Garcia |
| Status | ✅ COMPLETED |
| Task Type | Research/Analysis |
| Description | Review and analyze Jie Xu's quantum entanglement routing paper; identify core ML techniques |
| Key Findings | Adversarial Group Neural Bandits combining EXP3 + NeuralUCB |
| Deliverable | Documented literature analysis, framework comparison |
| Logged Time | 8-10 hours |
| Completion Date | August 25, 2025 |

Task 3: iCMAB Communication Channel Setup

| Property | Details |
| --- | --- |
| Task ID | T-2025-003 |
| Task Date/Time | September 3, 2025, Morning |
| Assigned By | Piter Garcia (Self) |
| Assigned To | Devroop Kar (Communication Partner) |
| Status | ✅ COMPLETED |
| Task Type | Collaboration/Administrative |
| Description | Establish communication channel with iCMAB developer for code access and integration questions |
| Action Taken | Initial email to Devroop Kar |
| Response Time | 5 days (Sep 8) |
| Deliverable | Active communication channel established |
| Logged Time | <1 hour |
| Completion Date | September 8, 2025 |

Task 4: GitHub Access & iCMAB Repository Setup

| Property | Details |
| --- | --- |
| Task ID | T-2025-004 |
| Task Date/Time | September 15, 2025, 7:59 AM - 10:45 AM |
| Assigned By | Devroop Kar |
| Assigned To | Piter Garcia |
| Status | ✅ COMPLETED |
| Task Type | Development/Setup |
| Description | Obtain GitHub access to iCMAB source code; add Piter to repository |
| GitHub Handle Provided | September 15, 10:45 AM |
| Response Time | 3 hours (same day) |
| Deliverable | Active GitHub access to iCMAB repository |
| Logged Time | 2-3 hours (setup + testing) |
| Completion Date | September 15, 2025 |

SEPTEMBER 2025

Task 5: Environment Stability & Health Recovery Coordination

| Property | Details |
| --- | --- |
| Task ID | T-2025-005 |
| Task Date/Time | September 18, 2025, 11:13 PM |
| Assigned By | Piter Garcia |
| Assigned To | Daniel Krutz |
| Status | ✅ COMPLETED |
| Task Type | Administrative/Health Management |
| Description | Request meeting reschedule due to environmental instability issue and health recovery needs |
| Issue Details | Introduced new adversarial attack variable; high sleep requirements (8+ hours); coursework deadlines |
| Original Meeting | Friday (Sep 20) |
| Rescheduled To | Monday, September 22, 7:30 AM |
| Response Time | <12 hours |
| Deliverable | Meeting rescheduled; environment issues addressed over weekend |
| Logged Time | Recovery time + 10 hours weekend work |
| Completion Date | September 22, 2025 |

Task 6: Process Improvement - Meeting Confirmation System

| Property | Details |
| --- | --- |
| Task ID | T-2025-006 |
| Task Date/Time | September 26, 2025 |
| Assigned By | Piter Garcia |
| Assigned To | Both (Piter & Dan) |
| Status | ✅ AGREED |
| Task Type | Process Improvement |
| Description | Establish process to confirm all meetings with calendar invites; avoid future miscommunication |
| Implementation | Calendar invites sent after each confirmed meeting |
| Status | System now in place |
| Completion Date | September 26, 2025 |

OCTOBER 2025

Task 7: CMAB Baseline Testing - Phase 1

| Property | Details |
| --- | --- |
| Task ID | T-2025-007 |
| Task Date/Time | October 3, 2025, 6:45 AM |
| Assigned By | Implicit (Research Plan) |
| Assigned To | Piter Garcia |
| Status | ✅ COMPLETED |
| Task Type | Research/Testing |
| Description | Comprehensive contextual MAB baseline testing across varying run configurations |
| Configurations Tested | 3, 5, 8, and 10 run setups |
| Key Results | CPursuit: 94.4%, CEpsilonGreedy: 92.4%, CThompsonSampling: 88.7% |
| Performance Gain | 15-20% improvement over baseline neural models |
| Statistical Validation | p < 0.001 |
| Logged Time | 40-50 hours |
| Completion Date | October 3, 2025 |

Task 8: iCMAB Algorithm Evaluation - Phase 2

| Property | Details |
| --- | --- |
| Task ID | T-2025-008 |
| Task Date/Time | October 3-16, 2025 |
| Assigned By | Research Plan |
| Assigned To | Piter Garcia |
| Status | ✅ COMPLETED |
| Task Type | Research/Testing |
| Description | Evaluate iCMAB versions of top-performing algorithms using same robust methodology |
| Algorithms Tested | iCPursuitNeuralUCB, iCEpsilonGreedy, ICEXP4, iCThompsonSampling |
| Key Finding | iCPursuitNeuralUCB: 81.4% average efficiency (multi-run validated) |
| Result Pattern | 91.7% of runs ≥70% efficiency; 100% ≥75% in final runs |
| Logged Time | 35-40 hours |
| Completion Date | October 16, 2025 |

Task 9: Framework Development - Production-Ready Architecture

| Property | Details |
| --- | --- |
| Task ID | T-2025-009 |
| Task Date/Time | October 10-21, 2025 |
| Assigned By | Research Requirements |
| Assigned To | Piter Garcia |
| Status | ✅ COMPLETED |
| Task Type | Development |
| Description | Build robust, production-ready evaluation framework addressing stability and reproducibility |
| Architecture Components | Multi-Run Evaluator, Qubit Allocator (4 strategies), Experiment Runner, Model Suite |
| Allocator Strategies | Fixed Baseline, Random, Dynamic UCB, Thompson Sampling |
| Models Supported | Oracle, GNeuralUCB, EXPNeuralUCB, CPursuitNeuralUCB, iCPursuitNeuralUCB |
| Key Features | Modular routing, deterministic reproducibility, automatic retry/validation, comprehensive logging |
| Best Result | Thompson Sampling: 94.97% efficiency |
| Logged Time | 60-80 hours |
| Completion Date | October 21, 2025 |

Task 10: Dynamic Qubit Allocation Strategy Comparison

| Property | Details |
| --- | --- |
| Task ID | T-2025-010 |
| Task Date/Time | October 21, 2025 |
| Assigned By | Framework Validation |
| Assigned To | Piter Garcia |
| Status | ✅ COMPLETED |
| Task Type | Analysis |
| Description | Compare performance across four qubit allocation strategies |
| Thompson Sampling | 94.97% efficiency (best) |
| Dynamic UCB | 94.68-94.92% at 6000 frames |
| Random Baseline | 75.44% (validates sophistication needed) |
| Key Insight | Intelligent routing provides 15-25% gains over random |
| Logged Time | 8-10 hours |
| Completion Date | October 21, 2025 |

Task 11: Paper Initiation & Structure Guidance

| Property | Details |
| --- | --- |
| Task ID | T-2025-011 |
| Task Date/Time | October 15, 2025, 6:57 AM |
| Assigned By | Daniel Krutz |
| Assigned To | Piter Garcia |
| Status | 🔄 IN PROGRESS (Core Writing Complete) |
| Task Type | Writing |
| Description | Paper write-up for quantum MAB research with structured guidance |
| Key Assignments | Research Questions, Related Works (5-10 papers), editable sections |
| Reference Papers | https://arxiv.org/pdf/2411.00316, https://arxiv.org/pdf/2404.09048 |
| Current Status | Core writing 90% complete |
| Logged Time | 100+ hours |

Task 12: Family Emergency Management

| Property | Details |
| --- | --- |
| Task ID | T-2025-012 |
| Task Date/Time | October 16, 2025, 1:51 AM |
| Assigned By | Circumstance |
| Assigned To | Piter Garcia |
| Status | ✅ HANDLED PROFESSIONALLY |
| Task Type | Personal/Administrative |
| Description | Father's hospitalization; manage work-life balance and communication |
| Situation | 48+ hours without sleep; uncertain schedule |
| Research Progress Despite Emergency | Completed 24 valid iCPursuitNeuralUCB runs; documented results |
| Advisor's Response | Priority set on family (all tasks secondary) |
| Recovery | Situation managed professionally and with support |
| Follow-up | October 21 status confirmed situation under control |
| Logged Time | N/A (personal priority) |
| Completion Date | Ongoing |

Task 13: Image Modification for Paper

| Property | Details |
| --- | --- |
| Task ID | T-2025-013 |
| Task Date/Time | October 28, 2025 |
| Assigned By | Daniel Krutz |
| Assigned To | Piter Garcia |
| Status | ✅ COMPLETED |
| Task Type | Design/Paper Preparation |
| Description | Modify existing image: remove attacker icon/X, label paths as "stochastic" |
| Purpose | Convert image from adversarial context to stochastic demonstration |
| Completion Date | November 3, 2025 |
| Flexibility | Piter offered further modifications if needed |
| Logged Time | 3-4 hours |

NOVEMBER 2025

Task 14: EXA-GP Framework Direction Assessment

| Property | Details |
| --- | --- |
| Task ID | T-2025-014 |
| Task Date/Time | November 12, 2025, 6:11 AM |
| Assigned By | Daniel Krutz |
| Assigned To | Piter Garcia |
| Status | ✅ COMPLETED & APPROVED |
| Task Type | Strategic Planning |
| Description | Assess EXA-GP framework direction and strategic alignment with existing quantum routing framework |
| Assessment Result | APPROVED - "Very solid idea" |
| Alignment Findings | Natural progression of existing framework, not a pivot |
| Architecture Fit | Framework already structured to support multiple interchangeable policy learners |
| Decision | Formalize EXA-GP as next phase direction |
| Logged Time | 8-10 hours |
| Completion Date | November 12, 2025 |

Task 15: Paper Structure & Related Works Compilation

| Property | Details |
| --- | --- |
| Task ID | T-2025-015 |
| Task Date/Time | November 15, 2025, 6:43 AM |
| Assigned By | Daniel Krutz |
| Assigned To | Piter Garcia |
| Status | 🔄 IN PROGRESS |
| Task Type | Writing |
| Description | Review paper comments in Overleaf; summarize and compare related works; follow IEEE paper structure |
| Reference Papers Provided | Multiple links shared in Overleaf |
| Current Status | Related works section drafted; comparisons in progress |
| Deliverable | Completed related works analysis |
| Logged Time | 25-30 hours (ongoing) |

Task 16: Top 5 Research Papers Identification

| Property | Details |
| --- | --- |
| Task ID | T-2025-016 |
| Task Date/Time | November 25, 2025, 6:48 AM |
| Assigned By | Daniel Krutz (implicitly) |
| Assigned To | Piter Garcia |
| Status | ✅ COMPLETED |
| Task Type | Research Analysis |
| Description | Identify and analyze top 5 papers for next-level research direction (EXA-GP integration) |
| Papers Identified | 5 key papers with strategic rationale |
| Paper 1 | Learning Best Paths in Quantum Networks (Wang et al., INFOCOM 2025) - BeQuP baseline |
| Paper 2 | Multipath Inter-Domain Routing (Li et al., IEEE ToN 2025) - QPSEL scalability |
| Paper 3 | EXA-GP / Evolutionary Graph-Based GP (Desell et al.) - Methodological anchor |
| Paper 4 | Best-of-Both-Worlds Bandits (Zimmert & Seldin, NeurIPS 2019) - Hybrid framework |
| Paper 5 | Equality of Opportunity in ML (Hardt et al., NeurIPS 2016) - Multi-objective design |
| Strategic Vision | EXA-GP as interpretable alternative on equal footing with neural methods |
| Logged Time | 12-15 hours |
| Completion Date | November 25, 2025 |

Task 17: Concise Problem & Solution Statements

| Property | Details |
| --- | --- |
| Task ID | T-2025-017 |
| Task Date/Time | November 25, 2025, 10:42 AM |
| Assigned By | Daniel Krutz |
| Assigned To | Piter Garcia |
| Status | ✅ COMPLETED |
| Task Type | Writing |
| Description | Provide 2-3 sentence answers to core research questions |
| Question 1 | Specific quantum network challenge for path selection |
| Answer 1 | Multi-hop entanglement routing maintaining high fidelity in noisy, lossy networks with online adaptation |
| Question 2 | ML aspect for unique quantum problem |
| Answer 2 | Adversarial Group Neural Bandits combining neural networks with multi-armed bandit decision-making |
| Logged Time | 4-6 hours |
| Completion Date | December 1, 2025 |

Task 18: Project Updates & Progress Meetings

| Property | Details |
| --- | --- |
| Task ID | T-2025-018 |
| Task Date/Time | November 17-18, 2025 |
| Assigned By | Devroop Kar |
| Assigned To | Piter Garcia |
| Status | ✅ COMPLETED |
| Task Type | Communication/Collaboration |
| Description | Progress update meeting with Devroop Kar regarding testing and results |
| Meeting Date | November 18, 2025, 12:30 PM |
| Participants | Piter Garcia, Devroop Kar |
| Topics Discussed | Framework progress, testing results, iCMAB integration |
| Logged Time | 1 hour (meeting) + 2 hours (prep) |
| Completion Date | November 18, 2025 |

DECEMBER 2025

Task 19: Quantum Project Documentation Suite

| Property | Details |
| --- | --- |
| Task ID | T-2025-019 |
| Task Date/Time | December 5, 2025, 2:33 PM |
| Assigned By | Devroop Kar (implied) |
| Assigned To | Piter Garcia |
| Status | ✅ COMPLETED |
| Task Type | Documentation |
| Description | Create comprehensive documentation enabling experimentation on Colab, local, and GCP |
| Documents Created | README.md, SETUP_COLAB.md, SETUP_LOCAL.md, TROUBLESHOOTING.md |
| Colab Runtime | 10-45 minutes depending on config |
| Local Setup Time | ~15 minutes |
| Key Features | Shared data lake, automatic checkpointing, registry system, cold-start optimization |
| Logged Time | 20-25 hours |
| Completion Date | December 5, 2025 |

Task 20: Comprehensive Testing Suite Development

| Property | Details |
| --- | --- |
| Task ID | T-2025-020 |
| Task Date/Time | December 10, 2025 |
| Assigned By | Daniel Krutz (feedback-based) |
| Assigned To | Piter Garcia |
| Status | 🔄 IN PROGRESS (3 of ~5 complete) |
| Task Type | Research/Testing |
| Description | Create and run comparison test cases based on identified literature papers |
| Test Plan | At least 2 tests this week (Dec); ~5 total by next week |
| Test Basis | Comparisons with BeQuP, LinkSelFiE, QPSEL, and other baselines |
| Deliverables | Data validation, benchmark design figures, result summary figures |
| Tests Completed | 3 major test suites |
| Logged Time | 40+ hours |

Task 21: Paper Evaluation Data & Figure Preparation

| Property | Details |
| --- | --- |
| Task ID | T-2025-021 |
| Task Date/Time | December 20, 2025 |
| Assigned By | Daniel Krutz (feedback-based) |
| Assigned To | Piter Garcia |
| Status | ✅ COMPLETED |
| Task Type | Research/Design |
| Description | Validate evaluation outputs; create curated validation corpus; build figures for paper |
| Deliverables | Validated output corpus, curated validation corpus in Drive, benchmark design figures, result summary figures |
| Status Report | "Validated evaluation outputs", "Created curated validation corpus", "Added key figures to Overleaf draft" |
| Logged Time | 15-20 hours |
| Completion Date | December 22, 2025 |

Task 22: Testbed Completion & Finalization

| Property | Details |
| --- | --- |
| Task ID | T-2025-022 |
| Task Date/Time | December 10-22, 2025 |
| Assigned By | Research Plan |
| Assigned To | Piter Garcia |
| Status | 🔄 IN PROGRESS (~70% complete) |
| Task Type | Research/Testing |
| Description | Finalize testbed evaluation infrastructure; wrap up two testbeds in progress |
| Status Report | "Paused mid-way to focus on comparison work; Still need to wrap up two testbeds in progress" |
| Timeline Note | Paused intentionally to prioritize paper comparisons |
| Logged Time | 25+ hours |

Task 23: Paper Comparisons to IEEE Baseline

| Property | Details |
| --- | --- |
| Task ID | T-2025-023 |
| Task Date/Time | December 20-22, 2025 |
| Assigned By | Daniel Krutz (feedback-based) |
| Assigned To | Piter Garcia |
| Status | 🔄 IN PROGRESS (~60% complete) |
| Task Type | Writing/Analysis |
| Description | Create direct apples-to-apples comparison to IEEE paper baseline results |
| Status Report | "Core comparator framing in place", "Evaluation infrastructure solid", "Direct apples-to-apples alignment to IEEE paper still in progress" |
| Timeline Note | Core infrastructure complete; detailed alignment work ongoing |
| Logged Time | 20+ hours |

JANUARY 2026

Task 24: Health Recovery & Wellness Management

| Property | Details |
| --- | --- |
| Task ID | T-2026-001 |
| Task Date/Time | December 31, 2025 - January 2, 2026 |
| Assigned By | Circumstance |
| Assigned To | Piter Garcia |
| Status | ✅ RECOVERED (January 7) |
| Task Type | Personal/Health |
| Description | Recovery from 3-day illness; manage work resumption timeline |
| Health Impact | Temporary work pause (3 days) |
| Advisor Support | Check-in (Jan 5), supportive tone |
| Recovery Status | "Slowly recovering---finally able to get out of bed" (Jan 7) |
| Completion Date | January 7, 2026 |

Task 25: GA Schedule Preparation & Documentation

| Property | Details |
| --- | --- |
| Task ID | T-2026-002 |
| Task Date/Time | January 7, 2026, 1:29 AM |
| Assigned By | Self-Assigned |
| Assigned To | Piter Garcia |
| Status | 🔄 IN PROGRESS |
| Task Type | Administrative |
| Description | Resume putting together GA schedule, especially around GA responsibilities |
| Notes | Resumed after health recovery; priority on documenting work hours and responsibilities |
| Logged Time | ~10 hours (work in progress) |

Task 26: Overleaf Project Consolidation & Clarification

| Property | Details |
| --- | --- |
| Task ID | T-2026-003 |
| Task Date/Time | January 7, 2026, 5:59 AM |
| Assigned By | Daniel Krutz |
| Assigned To | Piter Garcia |
| Status | ✅ CLARIFIED |
| Task Type | Project Management |
| Description | Clarify Overleaf project structure; consolidate if multiple versions exist |
| Finding | Single source (original project); secondary version for Travis review |
| Consolidation Status | Awaiting Travis feedback before consolidation |
| Logged Time | <1 hour |
| Completion Date | January 7, 2026 |

Task 27: Team Meeting Alignment & Next Steps

| Property | Details |
| --- | --- |
| Task ID | T-2026-004 |
| Task Date/Time | January 7, 2026, 4:53 PM |
| Assigned By | Piter Garcia |
| Assigned To | Team (Piter, Dan, Devroop, Sheeraja) |
| Status | 🔄 SCHEDULED |
| Task Type | Communication/Planning |
| Description | Team meeting to align project direction and next steps post-recovery |
| Scheduled Date/Time | Thursday, January 8, 2026, 2:00 PM |
| Participants | Piter Garcia, Daniel Krutz, Devroop Kar, Sheeraja |
| Objectives | Align on project priorities, EXA-GP direction, paper finalization path |
| Invitation Status | Dan invited to join; awaiting confirmation |

Task 28: Travis Feedback Follow-up

| Property | Details |
| --- | --- |
| Task ID | T-2026-005 |
| Task Date/Time | January 7, 2026 (Ongoing) |
| Assigned By | Daniel Krutz (implicit) |
| Assigned To | Piter Garcia |
| Status | ⏳ PENDING |
| Task Type | Communication/Feedback Integration |
| Description | Follow up with Professor Travis for feedback on cleaned Overleaf version |
| Target Timeline | This week (Jan 8-10) |
| Purpose | Feedback to drive next revision round |
| Logged Time | <1 hour (initial outreach) |

Task 29: Communication Tracking Document Maintenance

| Property | Details |
| --- | --- |
| Task ID | T-2026-006 |
| Task Date/Time | January 7, 2026, 4:53 PM (Ongoing) |
| Assigned By | Piter Garcia (Self) |
| Assigned To | Piter Garcia |
| Status | 🔄 IN PROGRESS |
| Task Type | Administrative |
| Description | Update Google Doc tracking all communications, feedback, and responses |
| Purpose | Centralized communication management; avoid back-and-forth confusion |
| Frequency | Ongoing (after major communications) |
| Logged Time | 2-3 hours |

SUMMARY BY TASK CATEGORY

Research & Framework Development (12 tasks)

- ✅ CMAB Baseline Testing (T-2025-007)

- ✅ iCMAB Algorithm Evaluation (T-2025-008)

- ✅ Framework Development (T-2025-009)

- ✅ Dynamic Qubit Allocation (T-2025-010)

- ✅ EXA-GP Assessment (T-2025-014)

- ✅ Top 5 Papers Analysis (T-2025-016)

- 🔄 Comprehensive Testing Suite (T-2025-020)

- 🔄 Paper Comparisons (T-2025-023)

- 🔄 Testbed Finalization (T-2025-022)

Writing & Documentation (8 tasks)

- ✅ Paper Initiation (T-2025-011) - Core Complete

- ✅ Paper Structure (T-2025-015) - In Progress

- ✅ Problem Statements (T-2025-017)

- ✅ Quantum Project Documentation (T-2025-019)

- ✅ Evaluation Data & Figures (T-2025-021)

- ✅ Image Modification (T-2025-013)

- 🔄 Testbed Documentation (Support)

Administrative & Coordination (7 tasks)

- ✅ GA Position Initiation (T-2025-001)

- ✅ iCMAB Communication Setup (T-2025-003)

- ✅ GitHub Access (T-2025-004)

- ✅ Meeting Confirmation Process (T-2025-006)

- ✅ Overleaf Consolidation (T-2026-003)

- 🔄 GA Schedule (T-2026-002)

- 🔄 Communication Tracking (T-2026-006)

Personal & Health Management (3 tasks)

- ✅ Family Emergency (T-2025-012)

- ✅ Health Recovery (T-2026-001)

- ⏳ Wellness Check (Dan's support)

Team & Collaboration (5 tasks)

- ✅ Environment Stability Coordination (T-2025-005)

- ✅ Project Updates Meeting (T-2025-018)

- 🔄 Team Meeting Alignment (T-2026-004)

- ⏳ Travis Feedback Follow-up (T-2026-005)

TIME ALLOCATION SUMMARY

| Category | Hours | % of Total |
| --- | --- | --- |
| Research & Testing | 180+ | 42% |
| Paper Writing & Editing | 130+ | 30% |
| Framework Development | 80+ | 19% |
| Documentation | 25+ | 6% |
| Administrative/Coordination | 20+ | 3% |
| TOTAL LOGGED | 435+ hours | 100% |

KEY METRICS

Completion Rates by Month

| Month | Tasks Logged | Completed | In Progress | % Complete |
| --- | --- | --- | --- | --- |
| Aug 2025 | 4 | 4 | 0 | 100% |
| Sep 2025 | 6 | 6 | 0 | 100% |
| Oct 2025 | 7 | 6 | 1 | 86% |
| Nov 2025 | 8 | 7 | 1 | 88% |
| Dec 2025 | 6 | 3 | 3 | 50% |
| Jan 2026 | 6 | 2 | 4 | 33% |
| TOTAL | 37 | 28 | 9 | 76% |

Response Times

| Type | Average Response Time |
| --- | --- |
| Clarifications | <1 hour |
| Feedback Requests | 2-4 hours |
| Major Tasks | 1-5 days |
| Meeting Scheduling | 1-2 messages |

CURRENT PROJECT STATUS (As of January 8, 2026)

Paper Writing: 90% Complete

- ✅ Core writing finalized

- ✅ Related works section drafted

- ✅ Problem statement defined

- ✅ ML approach specified

- ✅ Evaluation infrastructure complete

- 🔄 IEEE baseline comparisons in progress (~60%)

- ⏳ Testbed wrap-up needed (~30% remaining)

Framework: Production-Ready

- ✅ Architecture complete

- ✅ Multi-algorithm support (5+ models)

- ✅ Four qubit allocation strategies

- ✅ Robust testing infrastructure

- 🔄 EXA-GP integration pending

Documentation: Complete

- ✅ Quantum project documentation (4 guides)

- ✅ Multi-environment support (Colab/Local/GCP)

- ✅ Troubleshooting guide

- 🔄 Communication tracking document (in prep)

Team Collaboration: Active

- ✅ Weekly communication with Dan (established)

- ✅ Collaboration with Devroop (GitHub integration)

- 🔄 Full team alignment meeting scheduled (Jan 8, 2 PM)

- ⏳ Travis feedback awaiting follow-up

IMMEDIATE NEXT ACTIONS (Week of Jan 8-15)

- Thursday, Jan 8, 2 PM - Team alignment meeting (Piter, Dan, Devroop, Sheeraja)

- This Week - Follow up with Professor Travis for paper feedback

- Next 1-2 Weeks - Complete IEEE baseline comparisons

- Next 1-2 Weeks - Finalize remaining testbeds

- Post-feedback - Integrate Travis comments and prepare publication version

NOTES & OBSERVATIONS

Strengths Demonstrated

- Proactive Communication: Regular status updates and transparent about blockers

- Technical Excellence: High-quality framework development and testing methodology

- Resilience: Manages personal challenges while maintaining research momentum

- Collaboration: Effective three-way teamwork with Dan and Devroop

- Documentation: Creates usable, clear guides for reproducibility

Process Improvements Implemented

- Calendar-based meeting confirmation system

- Centralized communication tracking document

- Comprehensive documentation for multi-environment deployment

- Structured feedback integration process

Key Success Factors

- Clear advisor guidance (Dan's structured feedback)

- Strong collaboration support (Devroop's technical expertise)

- Proactive problem identification and resolution

- Health and well-being prioritized alongside research

- Documented progress and deliverables

Document Status: FINAL - Current as of January 8, 2026
Next Update: January 15, 2026 (post-team meeting)
Maintained By: Piter Garcia / Daniel Krutz
Distribution: Project Team (Piter, Dan, Devroop, Sheeraja)